## Final Timeline
ICT Orientation Virtual Tour
Project Planner: Alex Stewart
Review Date: 05/03/2024
Delivery Date: 18/06/2024
Phase | Tasks / Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date of Completion | Actual Date Completion | Variance (hrs)
Empathise | Investigate Project Details | 1 | 1 | 2024-03-02 | 2024-03-02 | 0
| Prepare the questions for the client | 1 | 1 | 2024-03-03 | 2024-03-03 | 0
| Interview with the Client | 1 | 1 | 2024-03-04 | 2024-03-08 | 0
| Document Client's Interview | 1 | 1 | 2024-03-05 | 2024-03-08 | 0
| Follow-up interview with the Client | 1 | 1 |  | NA | 0
Define | Analyse the Gathered Information from Interview | 2 | 2 | 2024-03-07 | 2024-03-09 | 0
| Prepare the Project Proposal | 2 | 3 | 2024-03-07 | 2024-03-11 | 1
| Define the Scope and Requirements of the Project | 1 | 2 | 2024-03-08 | 2024-03-11 | 1
| Create and identify User Personas | 1 | 3 | 2024-03-08 | 2024-03-12 | 2
| Research the appropriate Project Management Framework to use | 4 | 3 | 2024-03-08 | 2024-03-12 | -1
| Create the Project Plan, Timetable, Burndown Chart | 3 | 3 | 2024-03-12 | 2024-03-16 | 0
| Plan and Perform Risk Analysis | 3 | 2 | 2024-03-13 | 2024-03-11 | -1
| Plan the Tests for Quality Assurance | 3 | 4 | 2024-03-14 | 2024-03-19 | 1
| Identify the Ethical considerations | 2 | 2 | 2024-03-25 | 2024-03-26 | 0
| Finalise and submit Project Proposal Documentation | 2 | 5 | 2024-03-26 | 2024-03-30 | 3
Ideate | Ideation process (Generate and refine ideas) | 2 | 5 | 2024-03-29 | 2024-04-01 | 3
| Create Navigation Map for the website | 1 | 2 | 2024-03-29 | 2024-04-01 | 1
| Sketch an initial user interface | 1 | 1 | 2024-03-29 | 2024-04-02 | 0
| Determine the Design Features and Specification of the product | 2 | 3 | 2024-03-30 | 2024-04-03 | 1
| Gather the media assets / 360 pictures for Virtual Tour | 4 | 3 | 2024-03-30 | 2024-03-23 | -1
Lo-fi Prototyping / Testing | Interview users | 1 | 1 | 2024-03-30 | 2024-04-01 | 0
| Create Wireframe for the Website | 2 | 2 | 2024-03-30 | 2024-04-01 | 0
| Create Wireframe for the Virtual Tour | 3 | 3 | 2024-04-05 | 2024-04-01 | 0
| Implement the Functional Testing | 2 | 2 | 2024-04-06 | 2024-04-04 | 0
| Implement Usability Test with Target Users | 2 | 2 | 2024-04-07 | 2024-04-05 | 0
| Analysed the result of the Usability Testing | 1 | 2 | 2024-04-08 | 2024-04-11 | 1
| Refine and Improve Prototype based on the Testing Results | 2 | 2 | 2024-04-08 | 2024-04-11 | 0
| Finalise the Lo-fi Prototype For the Website and Virtual Tour | 2 | 2 | 2024-04-09 | 2024-04-11 | 0
| Perform and re-evaluate Risk Assessment | 2 | 2 | 2024-04-09 | 2024-04-12 | 0
| Document and submit Design Specification Draft | 2 | 2 | 2024-04-12 | 2024-04-12 | 0
Hi-fi Prototyping / Testing | Prepare all the media elements that will be used in the Website and Virtual Tour | 2 | 4 | 2024-05-03 | 2024-04-23 | 2
| Create Hi-fi Prototype for the Website and Virtual Tour | 4 | 4 | 2024-05-03 | 2024-04-23 | 0
| Implement and pass the Functional Testing | 1 | 3 | 2024-05-03 | 2024-04-23 | 2
| Implement Usability Test with Target Users | 1 | 1 | 2024-05-04 | 2024-04-25 | 0
| Refine and Improve Prototype based on the Testing Results | 2 | 2 | 2024-05-05 | 2024-04-25 | 0
| Plan the improvement for the next iteration. | 2 | 2 | 2024-05-06 | 2024-04-25 | 0
Hi-fi Prototyping / Testing | Create the high-fidelity prototype of the Virtual Tour in Lapentor | 12 | 13 | 2024-05-10 | 2024-05-09 | 1
0
Hi-fi Prototyping / Testing | Implement and pass the Functional Testing for website and virtual tour | 2 | 2 | 2024-05-17 | 2024-05-09 | 0
| Implement Usability Test with Target Users for website and virtual tour | 2 | 1 | 2024-05-18 | 2024-05-12 | -1
| Refine and Improve Prototype based on the Testing Results | 2 | 2 | 2024-05-18 | 2024-05-15 | 0
| Finalise the Hi-fi Prototype for the Virtual Tour | 2 | 2 | 2024-05-19 | 2024-05-16 | 0
| Prepare for the presentation of the Hi-fidelity prototype to the Client | 1 | 1 | 2024-05-24 | 2024-05-17 | 0
| Finalise and Deliver the Documentation of the Prototyping and Testing | 5 | 3 | 2024-05-28 | 2024-05-25 | -2
| Hand over prototype. | 1 | 0.5 | 2024-05-28 | 2024-05-25 | -0.5
Product Implementation / Final Testing | Perform and Re-evaluate Risk Assessment | 1 | 0 | 2024-06-01 | 2024-05-28 | 0
| Refinement of the Website Features and Functionality | 9 | 6 | 2024-06-05 | 2024-06-05 | -3
| Refinement of the Virtual Tour Features and Functionality | 5 | 1.5 | 2024-06-08 | 2024-06-05 | -3.5
| Final Functionality Testing | 3 | 1 | 2024-06-10 | 2024-06-10 | -2
| Final Usability Testing with Users | 3 | 2 | 2024-06-11 | 2024-06-10 | -1
| Create the Final Specification for the Product | 2 | 2 | 2024-06-12 | 2024-06-12 | 0
| Quality assurance implementation | 1 | 2 | 2024-06-12 | 2024-06-12 | 1
| Create Poster for the Project | 3 | 2 | 2024-06-17 | 2024-06-12 | -1
| Project Documentation | 5 | 3 | 2024-06-13 | 2024-06-13 | -2
| Submit all the deliverables and documentation | 1 | 1 | 2024-06-18 | 2024-06-18 | 0
| Deploy a functional and usable final product | 1 | 1 | 2024-06-18 | 2024-06-18 | 0
| Total time | 130 | 130 |  | Total Variance | 0